## Sheet1
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Requirement Analysis | MUST HAVE | No Dependency | Y R Rahul, Vijay Kanigiri , Yashas B R , Sriram Vennampalli, Usha Rao Patteti, Somireddi Sai Kiran | 3 - Completed
S1 | S1 | US-002 | Finalize Technology Stack (React, Node js, APIs) | MUST HAVE | Research Tech Evaluation | Y R Rahul, Vijay Kanigiri , Yashas B R , Sriram Vennampalli, Usha Rao Patteti, Somireddi Sai Kiran | 3 - Completed
S1 | S1 | US-003 | System Architecture Design | MUST HAVE | Architecture Planning | Y R Rahul, Vijay Kanigiri , Yashas B R , Sriram Vennampalli, Usha Rao Patteti, Somireddi Sai Kiran | 3 - Completed
S1 | S2 | US-004 | GitHub Repository & Project Structure Setup | MUST HAVE | GitHub | Y R Rahul, Vijay Kanigiri , Yashas B R , Sriram Vennampalli, Usha Rao Patteti, Somireddi Sai Kiran | 3 - Completed
S2 | S2 | US-005 | Custom Purpule Theme Implementation | MUST HAVE | Tailwind CSS | Y R Rahul, Usha Rao Patteti, VijayKanigiri | 3 - Completed
S2 | S2 | US-006 | Supabase / REST API Layer Integration | MUST HAVE | Supabase | Sriram Vennampalli, Y R Rahul | 3 - Completed
S2 | S2 | US-007 | PostgreSQL Database Configuration | MUST HAVE | PostgreSQL | Somireddi Sai Kiran,Usha, Vijay Kanigiri | 3 - Completed
S3 | S3 | US-008 | Real-time Threat Detection Dashboard | MUST HAVE | React.js, PostgreSQL | Y R Rahul, Sriram Vennampalli, Usha Rao Patteti | 3 - Completed
S3 | S3 | US-009 | Geospatial Attack Map Implementation | MUST HAVE | Leaflet.js Map Visualization | Y R Rahul, Yashas B R, Usha Rao Patteti | 3 - Completed
S3 | S3 | US-010 | Data Ingestion Pipeline (CSV, JSON, REST) | MUST HAVE | PostgreSQL, REST API | Vijay,Somireddi Sai Kiran, Sriram Vennampalli | 3 - Completed
S3 | S4 | US-011 | Gemini Integration for Threat Summarization | MUST HAVE | Gemini-3-flash API | Somireddi Sai Kiran, Vijay Kanigiri, Yashas B R | 3 - Completed
S4 | S4 | US-012 | Nmap Scanner Integration (Quick, Full, SYN, Service Detection) | MUST HAVE | Nmap | Sriram Vennampalli, Y R Rahul | 3 - Completed
S4 | S5 | US-013 | IP Agent AI Chatbot | MUST HAVE | Gemini API | Somireddi Sai Kiran, Vijay Kanigiri, Yashas B R | 3 - Completed
S4 | S5 | US-014 | Auto-Block Engine for Critical Threats | MUST HAVE | PostgreSQL | Y R Rahul, Usha Rao Patteti | 3 - Completed
S4 | S5 | US-015 | Data Preprocessing Pipeline | MUST HAVE | PostgreSQL | Y R Rahul, Vijay Kanigiri , Yashas B R , Sriram Vennampalli, Usha Rao Patteti, Somireddi Sai Kiran | 3 - Completed
S5 | S6 | US-016 | System Architecture Diagram Display | MUST HAVE | React.js | Usha Rao Patteti, Vijay Kanigiri | 3 - Completed
S5 | S6 | US-017 | REST API Endpoints for Threat Data | MUST HAVE | Supabase, REST API | Sriram Vennampalli, Yashas B R | 3 - Completed
S5 | S6 | US-018 | Live API Stream Integration | MUST HAVE | REST API, Live Stream | Somireddi Sai Kiran, Vijay Kanigiri | 3 - Completed
S6 | S6 | US-019 | Deployment on Lovable.app Cloud Platform | MUST HAVE | Lovable.app | Y R Rahul | 3 - Completed
S6 | S7 | US-020 | CSV, JSON Data Format Support | MUST HAVE | CSV, JSON | Yashar B R ,Vijay Kanigiri | 3 - Completed
S6 | S7 | US-021 | Complete Integration Testing | MUST HAVE | Complete System | Y R Rahul, Vijay Kanigiri , Yashas B R , Sriram Vennampalli, Usha Rao Patteti, Somireddi Sai Kiran | 3 - Completed
S7 | S8 | US-022 | System testing | MUST HAVE | Complete System | Y R Rahul, Vijay Kanigiri , Yashas B R , Sriram Vennampalli, Usha Rao Patteti, Somireddi Sai Kiran | 3 - Completed
S7 | S8 | US-023 | Bug fixing | MUST HAVE | Complete System | Y R Rahul,Usha Rao Patteti, Sriram Vennampalli | 3 - Completed
S7 | S8 | US-024 | Agile Documention | MUST HAVE | Sprint Records | Usha Rao Patteti | 3 - Completed